## 1. Reconciliation
Issue ID | Title | Classification | Parent | Reason | Final Severity
MAF-TECH-001 | robots.txt returns HTML SPA shell | UNIQUE | — | Standalone finding | CRITICAL
MAF-TECH-003 | No canonical link tag | UNIQUE | — | Standalone finding | CRITICAL
MAF-TECH-012 | Full CSR — content invisible without JS | UNIQUE | — | Standalone finding | CRITICAL
MAF-TECH-027 | No structured data (JSON-LD) | UNIQUE | — | Standalone finding | CRITICAL
MAF-TECH-036 | Arabic content not discoverable (state i18n) | UNIQUE | — | Standalone finding | CRITICAL
MAF-TECH-002 | No XML sitemap | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-004 | Index status unverifiable | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-005 | All paths HTTP 200 (soft-404) | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-006 | No HTTP→HTTPS, non-www→www redirects | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-013 | No code splitting | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-017 | No OG/Twitter Card tags | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-018 | JS bundle too large (~2.5MB) | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-019 | No browser/CDN caching | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-022 | Estimated poor LCP (>2.5s) | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-023 | Estimated poor TBT (>200ms) | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-038 | html lang="en" hardcoded | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-049 | Missing critical security headers | UNIQUE | — | Standalone finding | HIGH
MAF-TECH-008 | Potential crawl trap | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-009 | /blog returns 404 | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-011 | Blog post routes unverified | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-020 | Cloudflare edge cache unused | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-021 | Assets lack long-cache URLs | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-024 | Font loading not optimized | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-025 | Same large bundle on mobile | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-026 | Mobile-first indexing readiness (CSR) | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-028 | Missing sameAs/social URLs | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-030 | No cookie consent | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-032 | No accessibility statement [T051 merged] | UNIQUE (canonical) | — | T051 merged into T032 — duplicate finding from different specialist agents | MEDIUM
MAF-TECH-040 | Conversion events unverifiable | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-042 | Logo too large (~307KB) | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-043 | Portfolio images unverified | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-044 | No responsive images/WebP | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-046 | Google Fonts render-blocking | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-050 | A11y baseline unverifiable (CSR) | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-052 | Technical debt accumulating | UNIQUE | — | Standalone finding | MEDIUM
MAF-TECH-010 | No dedicated contact page | UNIQUE | — | Standalone finding | LOW
MAF-TECH-031 | No Terms & Conditions | UNIQUE | — | Standalone finding | LOW
MAF-TECH-033 | No .ico favicon | UNIQUE | — | Standalone finding | LOW
MAF-TECH-034 | No web app manifest | UNIQUE | — | Standalone finding | LOW
MAF-TECH-035 | System paths return SPA shell | UNIQUE | — | Standalone finding | LOW
MAF-TECH-039 | No analytics in raw HTML | UNIQUE | — | Standalone finding | LOW
MAF-TECH-041 | No lead capture forms | UNIQUE | — | Standalone finding | LOW
MAF-TECH-045 | Favicon MIME type mismatch | UNIQUE | — | Standalone finding | LOW
MAF-TECH-047 | Google Fonts not self-hosted | UNIQUE | — | Standalone finding | LOW
MAF-TECH-048 | HSTS header not set ⚠️ SUB-ITEM of T049 | SUB-ITEM | MAF-TECH-049 | HSTS is one component of T049's missing security headers; fixed by same AR-007 | SUB-ITEM

## 2. HML Matrix
| Issue ID | Severity | Priority | Title | Root Cause | Phase | Gap Type | Artifact
1 | MAF-TECH-001 | CRITICAL | P0 | robots.txt returns HTML SPA shell | B | 1 | ✅ VERIFIED | AR-001,AR-003
2 | MAF-TECH-003 | CRITICAL | P0 | No canonical link tag | E | 1 | ✅ VERIFIED | AR-008
3 | MAF-TECH-012 | CRITICAL | P0 | Full CSR — content invisible without JS | A | 2 | ⚠️ PARTIAL — CSR mitigated, no SSR | AR-008,009,013,014 (SSR cancelled AR-016)
4 | MAF-TECH-027 | CRITICAL | P0 | No structured data (JSON-LD) | A/E | 2 | ✅ CODE DONE — Rich Results validation pending | AR-009,010,011
5 | MAF-TECH-036 | CRITICAL | P0 | Arabic content not discoverable (state i18n) | A/D | 2 | ✅ VERIFIED | AR-013,014
6 | MAF-TECH-002 | HIGH | P1 | No XML sitemap | B | 1 | ✅ VERIFIED | AR-002,003
7 | MAF-TECH-004 | HIGH | P1 | Index status unverifiable | Gap | — | ⚠️ NEEDS GSC | —
8 | MAF-TECH-005 | HIGH | P1 | All paths HTTP 200 (soft-404) | B | 1 | ⚠️ PARTIAL — probe 404 + noindex | AR-005
9 | MAF-TECH-006 | HIGH | P1 | No HTTP→HTTPS, non-www→www redirects | B | 1 | ✅ VERIFIED | AR-004
10 | MAF-TECH-013 | HIGH | P2 | No code splitting | A | 2 | ✅ VERIFIED | AR-015
11 | MAF-TECH-017 | HIGH | P2 | No OG/Twitter Card tags | A | 2 | ✅ VERIFIED | AR-012
12 | MAF-TECH-018 | HIGH | P3 | JS bundle too large (~2.5MB) | A/C | 3 | ⚠️ PARTIAL — bundle reduced, measure post-deploy | (via T013)
13 | MAF-TECH-019 | HIGH | P1 | No browser/CDN caching | C | 1 | ✅ VERIFIED | AR-006
14 | MAF-TECH-022 | HIGH | P2 | Estimated poor LCP (>2.5s) | A | 2 | 📋 LAB ESTIMATE | (via T012)
15 | MAF-TECH-023 | HIGH | P2 | Estimated poor TBT (>200ms) | A | 2 | 📋 LAB ESTIMATE | (via T013)
16 | MAF-TECH-038 | HIGH | P2 | html lang="en" hardcoded | A/D | 2 | ✅ VERIFIED | AR-014
17 | MAF-TECH-049 | HIGH | P1 | Missing critical security headers | E | 1 | ✅ VERIFIED | AR-007
18 | MAF-TECH-008 | MEDIUM | P2 | Potential crawl trap | B | 1 | ⚠️ PARTIAL — probe 404 + noindex | AR-005
19 | MAF-TECH-009 | MEDIUM | P3 | /blog returns 404 | — | 3 | ✅ VERIFIED | —
20 | MAF-TECH-011 | MEDIUM | P3 | Blog post routes unverified | Gap | 3 | ⚠️ ANALYSIS GAP | —
21 | MAF-TECH-020 | MEDIUM | P2 | Cloudflare edge cache unused | C | 1 | ⚠️ PENDING EXTERNAL — Cloudflare UI rules | AR-006 (019/021 done; 020 pending Cloudflare)
22 | MAF-TECH-021 | MEDIUM | P2 | Assets lack long-cache URLs | C | 1 | ✅ VERIFIED | AR-006
23 | MAF-TECH-024 | MEDIUM | P3 | Font loading not optimized | C | 3 | ✅ VERIFIED | AR-017
24 | MAF-TECH-025 | MEDIUM | P2 | Same large bundle on mobile | A | 2 | ⚠️ PARTIAL — route splitting on mobile | AR-015
25 | MAF-TECH-026 | MEDIUM | P2 | Mobile-first indexing readiness (CSR) | Gap | 2 | ⚠️ ANALYSIS GAP | AR-016
26 | MAF-TECH-028 | MEDIUM | P2 | Missing sameAs/social URLs | Gap | — | 🏢 NEEDS BUSINESS | AR-009
27 | MAF-TECH-030 | MEDIUM | P3 | No cookie consent | E | 3 | ✅ VERIFIED | —
28 | MAF-TECH-032 | MEDIUM | P3 | No accessibility statement [T051 merged] | E | 3 | ✅ VERIFIED | —
29 | MAF-TECH-040 | MEDIUM | P2 | Conversion events unverifiable | Gap | — | ⚠️ NEEDS GA4 | —
30 | MAF-TECH-042 | MEDIUM | P3 | Logo too large (~307KB) | A | 3 | ✅ VERIFIED | AR-018
31 | MAF-TECH-043 | MEDIUM | P3 | Portfolio images unverified | Gap | 3 | ⚠️ ANALYSIS GAP | AR-018
32 | MAF-TECH-044 | MEDIUM | P3 | No responsive images/WebP | A/C | 3 | ✅ VERIFIED | AR-018
33 | MAF-TECH-046 | MEDIUM | P3 | Google Fonts render-blocking | C | 3 | ✅ VERIFIED | AR-017
34 | MAF-TECH-050 | MEDIUM | P2 | A11y baseline unverifiable (CSR) | A | 2 | ⚠️ ANALYSIS GAP | AR-016
35 | MAF-TECH-052 | MEDIUM | P2 | Technical debt accumulating | A | 2 | ⚠️ PARTIAL — debt reduced, CSR accepted | AR-016
36 | MAF-TECH-010 | LOW | P4 | No dedicated contact page | — | — | ✅ VERIFIED | —
37 | MAF-TECH-031 | LOW | P4 | No Terms & Conditions | — | — | 🏢 NEEDS BUSINESS | —
38 | MAF-TECH-033 | LOW | P4 | No .ico favicon | E | — | ✅ VERIFIED | —
39 | MAF-TECH-034 | LOW | P4 | No web app manifest | E | — | ✅ VERIFIED | —
40 | MAF-TECH-035 | LOW | P4 | System paths return SPA shell | B | 1 | ⚠️ PARTIAL — probe paths 404 | AR-005
41 | MAF-TECH-039 | LOW | P4 | No analytics in raw HTML | Gap | — | N/A — BY DESIGN (consent-gated analytics) | —
42 | MAF-TECH-041 | LOW | P4 | No lead capture forms | — | — | ✅ VERIFIED | —
43 | MAF-TECH-045 | LOW | P4 | Favicon MIME type mismatch | E | — | ✅ VERIFIED | —
44 | MAF-TECH-047 | LOW | P4 | Google Fonts not self-hosted | C | — | ✅ CODE DONE — fonts self-hosted Aug 2026 | AR-017 (024/046); 047 self-host separate
45 | MAF-TECH-048 | MEDIUM (sub) | P2 | HSTS header not set ⚠️ SUB-ITEM of T049 | E | 1 | ✅ VERIFIED | AR-007

## 3. Dev Decisions
Issue ID | Title | Severity | Dev Decision | Dev Comment | Date | Next Action
MAF-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Implemented a real robots.txt file served as plain text via nginx, replacing the previous SPA HTML response. [This tells Google which pages it may crawl — like a “welcome” sign for search engines instead of a blank page.] | 2026-08-18 | Verify on production after deploy (curl /robots.txt).
MAF-TECH-003 | No canonical link tag | CRITICAL | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Canonical link tags are injected per route for both /en and /ar pages, with a static fallback in index.html. [Each page now tells Google its “official” URL so duplicate-language versions are not confused.] | 2026-08-18 | Spot-check canonical on key pages after deploy.
MAF-TECH-012 | Full CSR — content invisible without JS | CRITICAL | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | We are keeping React (no SSR migration). Mitigated with static meta tags, JSON-LD in HTML, bilingual URLs, sitemap, and robots rules. Full page HTML without JavaScript is not in scope. [The site still loads content after scripts run, but we added the main SEO signals Google needs without rebuilding the whole site.] | 2026-08-18 | Monitor Google Search Console rendering after deploy; no SSR planned.
MAF-TECH-027 | No structured data (JSON-LD) | CRITICAL | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Structured data (JSON-LD) added: Organization in raw HTML; after load adds WebSite, BreadcrumbList, and BlogPosting on blog pages. [Rich search snippets — company info and breadcrumbs — can now appear in Google results.] | 2026-08-18 | Validate with Google Rich Results Test after deploy.
MAF-TECH-036 | Arabic content not discoverable (state i18n) | CRITICAL | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Dedicated /en/... and /ar/... URL routes implemented; language toggle updates the URL. hreflang tags and bilingual sitemap included. [Arabic and English now have separate web addresses Google can index independently.] | 2026-08-18 | Confirm hreflang in Search Console after deploy.
MAF-TECH-002 | No XML sitemap | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | XML sitemap created with all main pages in English and Arabic, linked from robots.txt. [A map of all site pages is available for Google to find and index faster.] | 2026-08-18 | Submit sitemap in Google Search Console (Marketing).
MAF-TECH-004 | Index status unverifiable | HIGH | ☐ APPROVE ☐ MODIFY ☐ REJECT ☑ FURTHER INVESTIGATION | Index status cannot be confirmed without Google Search Console access. This is an owner/marketing account task, not a development code fix. [We need login access to Google’s search dashboard to see if pages are actually appearing in search results.] | 2026-08-18 | Marketing: grant GSC access and submit sitemap.
MAF-TECH-005 | All paths HTTP 200 (soft-404) | HIGH | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Probe paths (wp-admin, etc.) return real HTTP 404 via nginx; unknown SPA routes get noindex meta. True HTTP 404 for every invalid React route would require SSR. [Fake “success” pages for hacker probes are blocked; remaining soft-404s are mitigated with “do not index” tags.] | 2026-08-18 | None — accepted partial mitigation.
MAF-TECH-006 | No HTTP→HTTPS, non-www→www redirects | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | HTTP to HTTPS and non-www to www redirects configured in deployment nginx. [Visitors are automatically sent to the secure, correct website address.] | 2026-08-18 | Verify redirects live after deploy.
MAF-TECH-013 | No code splitting | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Route-level code splitting implemented via Vite manualChunks and React.lazy for non-home pages. [The site loads smaller pieces of code per page so pages open faster.] | 2026-08-18 | Review bundle report after build if needed.
MAF-TECH-017 | No OG/Twitter Card tags | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Open Graph and Twitter Card meta tags added statically in index.html and updated dynamically per route via SeoProvider. [Links shared on social media now show proper title, description, and image previews.] | 2026-08-18 | Test share preview on LinkedIn/Facebook after deploy.
MAF-TECH-018 | JS bundle too large (~2.5MB) | HIGH | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Bundle size reduced through code splitting and vendor chunking. Remaining size is expected for a React SPA with animations. [The download is smaller than before, but a rich interactive site will always be heavier than a plain HTML page.] | 2026-08-18 | Monitor Lighthouse after deploy.
MAF-TECH-019 | No browser/CDN caching | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Browser and CDN cache headers configured: hashed assets cached 1 year; static SEO files have appropriate TTL; index.html set to no-store. [Repeat visitors load the site faster because their browser keeps copies of images and scripts.] | 2026-08-18 | Confirm Cache-Control headers on live site.
MAF-TECH-022 | Estimated poor LCP (>2.5s) | HIGH | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Lab-estimated LCP improved via code splitting, font preload/swap, WebP images, and animation optimization (including Mac performance fix). Full LCP target may still need SSR for first paint. [Main content should appear faster; exact speed should be measured on the live site.] | 2026-08-18 | Run PageSpeed Insights after deploy.
MAF-TECH-023 | Estimated poor TBT (>200ms) | HIGH | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Total Blocking Time improved via code splitting and reduced animation cost. React execution remains on the main thread by architecture. [The site freezes less on load, but some delay is normal for interactive React apps.] | 2026-08-18 | Measure TBT with Lighthouse after deploy.
MAF-TECH-038 | html lang="en" hardcoded | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | html lang and dir attributes update dynamically based on locale (/en or /ar) and localStorage before first paint. [The browser knows whether the page is English or Arabic for accessibility and search.] | 2026-08-18 | None.
MAF-TECH-049 | Missing critical security headers | HIGH | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Security headers added via nginx: X-Content-Type-Options, X-Frame-Options, Referrer-Policy, Permissions-Policy, and HSTS (also covers MAF-TECH-048). [Standard website security settings that protect visitors and improve trust signals.] | 2026-08-18 | Verify headers with securityheaders.com after deploy.
MAF-TECH-008 | Potential crawl trap | MEDIUM | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Crawl-trap risk mitigated same as MAF-TECH-005: probe paths return 404; unknown SPA pages get noindex. Full elimination of infinite SPA URLs needs SSR. [Search engines are steered away from junk paths; complete fix limited by React architecture.] | 2026-08-18 | None — accepted partial mitigation.
MAF-TECH-009 | /blog returns 404 | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | /blog permanently redirects to /en/blogs via nginx 301. [Old blog link bookmarks and external links still work.] | 2026-08-18 | None.
MAF-TECH-011 | Blog post routes unverified | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Blog post routes verified at /en/blogs/:slug and /ar/blogs/:slug. Missing slugs redirect to the blogs listing. [Individual blog articles have working addresses in both languages.] | 2026-08-18 | Marketing: publish test blog post and confirm URL.
MAF-TECH-020 | Cloudflare edge cache unused | MEDIUM | ☐ APPROVE ☐ MODIFY ☐ REJECT ☑ FURTHER INVESTIGATION | Origin cache headers (Cache-Control + CDN-Cache-Control) are implemented in nginx. Cloudflare dashboard cache rules still need to be applied — IT Dev prepared guide at deploy/cloudflare/CACHE_RULES.md (no separate Ops team). [The server is ready to cache; someone must click 3 rules in the Cloudflare website panel — about 5 minutes.] | 2026-08-18 | IT Dev or Marketing admin: apply 3 Cloudflare cache rules from CACHE_RULES.md.
MAF-TECH-021 | Assets lack long-cache URLs | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Vite produces content-hashed asset filenames with max-age=31536000 immutable cache headers. [Updated files get new names so browsers always fetch fresh code after a release.] | 2026-08-18 | None.
MAF-TECH-024 | Font loading not optimized | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Google Fonts loaded with display=swap and preload to reduce invisible text during load. [Text appears immediately with a fallback font, then switches to the brand font — no blank text.] | 2026-08-18 | None.
MAF-TECH-025 | Same large bundle on mobile | MEDIUM | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Route-level splitting reduces JavaScript downloaded on mobile for inner pages. React core bundle is still shared across all pages. [Mobile users get less code on sub-pages, but the base app size remains.] | 2026-08-18 | None.
MAF-TECH-026 | Mobile-first indexing readiness (CSR) | MEDIUM | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Same React app serves mobile and desktop; Google can render JavaScript for indexing. Further HTML-in-source improvement would require SSR, which is out of scope. [Google can read our mobile site; we stay on the current technology by choice.] | 2026-08-18 | Monitor mobile indexing in GSC (Marketing).
MAF-TECH-028 | Missing sameAs/social URLs | MEDIUM | ☐ APPROVE ☐ MODIFY ☐ REJECT ☑ FURTHER INVESTIGATION | JSON-LD sameAs field is wired to dashboard Static Info social URLs. Business/marketing must enter Instagram, Facebook, LinkedIn, and YouTube profile links. [The code is ready; marketing needs to paste the company’s social media links in the admin panel.] | 2026-08-18 | Marketing: fill social profile URLs in Admin Dashboard → Static Info.
MAF-TECH-030 | No cookie consent | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Cookie consent banner implemented with Accept/Reject; Google Analytics loads only after consent. Cookie Policy page added in EN/AR. [Visitors choose whether to allow tracking cookies — required for privacy compliance.] | 2026-08-18 | Legal/marketing to review cookie policy wording if needed.
MAF-TECH-032 | No accessibility statement [T051 merged] | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Accessibility statement pages created at /en/accessibility and /ar/accessibility, linked in footer. [A public page explaining our accessibility commitment — often required for compliance.] | 2026-08-18 | Marketing/legal to review statement content.
MAF-TECH-040 | Conversion events unverifiable | MEDIUM | ☐ APPROVE ☐ MODIFY ☐ REJECT ☑ FURTHER INVESTIGATION | Conversion tracking coded: contact form fires generate_lead; WhatsApp float button fires contact event. Marketing needs GA4 access to verify events appear in reports. [Tracking code is installed; marketing must confirm numbers show up in Google Analytics.] | 2026-08-18 | Marketing: verify generate_lead and contact events in GA4 Realtime.
MAF-TECH-042 | Logo too large (~307KB) | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Logo reduced to 40 KB PNG (256px) and 24 KB WebP — under 50 KB target. [Logo no longer slows pages.] | 2026-08-18 | None.
MAF-TECH-043 | Portfolio images unverified | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | New CMS uploads auto-compress via sharp (resize + WebP) before Cloudinary. Existing images use Cloudinary f_auto and srcset for responsive delivery. [Photos uploaded through the dashboard are automatically shrunk; old photos are served in optimal size.] | 2026-08-18 | Marketing: optionally re-upload very large legacy portfolio images.
MAF-TECH-044 | No responsive images/WebP | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Responsive images with WebP via Cloudinary transformations (f_auto, q_auto, srcset) on blog and portfolio components. Lazy loading already present. [Images automatically adjust to screen size and modern format for faster loading.] | 2026-08-18 | None.
MAF-TECH-046 | Google Fonts render-blocking | MEDIUM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Google Fonts render-blocking reduced with preload and display=swap (same fix as MAF-TECH-024). [Page text shows immediately instead of waiting for fonts.] | 2026-08-18 | None.
MAF-TECH-050 | A11y baseline unverifiable (CSR) | MEDIUM | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Accessibility statement page added. Full accessibility audit applies to the live rendered page (Lighthouse/axe), not raw HTML source — limited by React CSR architecture which we are keeping. [We added the required statement page; a full accessibility score test runs on the live site, not the code file alone.] | 2026-08-18 | Optional: run Lighthouse accessibility audit after deploy.
MAF-TECH-052 | Technical debt accumulating | MEDIUM | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Technical debt actively reduced while staying on React: bilingual URLs, code splitting, caching, cookie consent, T&C, image pipeline, performance fixes. Remaining CSR limitations are an accepted architectural choice, not unmanaged debt. [We cleaned up many issues without rebuilding the site; some limits remain because we chose to keep React.] | 2026-08-18 | None — ongoing maintenance as normal.
MAF-TECH-010 | No dedicated contact page | LOW | ☐ APPROVE ☐ MODIFY ☑ REJECT ☐ FURTHER INVESTIGATION | Audit finding is outdated — dedicated contact page already exists at /en/contact and /ar/contact with working form. [The contact page was already built; the audit missed it.] | 2026-08-18 | None.
MAF-TECH-031 | No Terms & Conditions | LOW | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | T&C page + admin editor live. Approved legal content entry pending Marketing/Legal. [Page built; legal text is business task.] | 2026-08-18 | Marketing/Legal: enter T&C content
MAF-TECH-033 | No .ico favicon | LOW | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | favicon.ico and favicon.svg added and served with correct nginx location. [The small icon in browser tabs now displays correctly.] | 2026-08-18 | None.
MAF-TECH-034 | No web app manifest | LOW | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | site.webmanifest created and served with correct MIME type via nginx. [Enables “add to home screen” on mobile and proper PWA metadata.] | 2026-08-18 | None.
MAF-TECH-035 | System paths return SPA shell | LOW | ☐ APPROVE ☑ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Common probe paths (wp-admin, admin, .env, phpmyadmin) return real HTTP 404 via nginx. Other unknown SPA URLs still return 200 with noindex — same limitation as MAF-TECH-005. [Hacker probe addresses are blocked; random invalid URLs still show a “not found” page without a server error.] | 2026-08-18 | None — accepted partial mitigation.
MAF-TECH-039 | No analytics in raw HTML | LOW | ☐ APPROVE ☐ MODIFY ☑ REJECT ☐ FURTHER INVESTIGATION | Analytics intentionally not in raw HTML — must load only after cookie consent per MAF-TECH-030 and privacy policy. Injecting gtag before consent would violate our cookie compliance. [Tracking scripts wait for user permission, which is correct for privacy law.] | 2026-08-18 | None.
MAF-TECH-041 | No lead capture forms | LOW | ☐ APPROVE ☐ MODIFY ☑ REJECT ☐ FURTHER INVESTIGATION | Audit finding is outdated — contact form and Google Calendar booking integration already exist on the contact page. [Lead capture was already built; audit did not check current site.] | 2026-08-18 | None.
MAF-TECH-045 | Favicon MIME type mismatch | LOW | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Favicon MIME types corrected: .ico served as icon, .svg as image/svg+xml — no longer PNG mislabeled as SVG. [Browser receives the icon in the correct file format.] | 2026-08-18 | None.
MAF-TECH-047 | Google Fonts not self-hosted | LOW | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | Fonts self-hosted via @fontsource — no Google Fonts requests on public site. [Privacy and performance improved; no external font dependency.] | 2026-08-18 | None.
MAF-TECH-048 | HSTS header not set ⚠️ SUB-ITEM of T049 | SUB-ITEM | ☑ APPROVE ☐ MODIFY ☐ REJECT ☐ FURTHER INVESTIGATION | HSTS header set in HTTPS nginx configuration as sub-item of MAF-TECH-049. [Browsers are told to always use the secure HTTPS version.] | 2026-08-18 | None.

## 4. Impl Tracker
Issue ID | Title | Severity | Phase | Impl Status | Impl Owner | Target Date | Started | Completed | Notes
MAF-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Added website/public/robots.txt and nginx exact location block. Completed Aug 2026. [Search engines now receive proper crawl instructions.]
MAF-TECH-003 | No canonical link tag | CRITICAL | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | SeoProvider + static canonical in index.html. [Official page addresses are set automatically.]
MAF-TECH-012 | Full CSR — content invisible without JS | CRITICAL | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | CSR architecture retained by business decision. Partial SEO mitigations applied. [We improved search visibility within the current website technology.]
MAF-TECH-027 | No structured data (JSON-LD) | CRITICAL | Phase 2 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | index.html Organization schema + SeoProvider dynamic JSON-LD. [Search engines get structured company and page data.]
MAF-TECH-036 | Arabic content not discoverable (state i18n) | CRITICAL | Phase 2 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Locale routing, redirects from legacy URLs, sitemap + hreflang. [Arabic content is now discoverable via its own links.]
MAF-TECH-002 | No XML sitemap | HIGH | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | website/public/sitemap.xml with en/ar URLs. [Complete page list for search engines.]
MAF-TECH-004 | Index status unverifiable | HIGH | — | PENDING | Marketing | 2026-08-18 | 2026-08-11 |  | Sitemap and SEO fixes are ready; verification blocked on GSC access. [Dev work done; marketing must check Google’s side.]
MAF-TECH-005 | All paths HTTP 200 (soft-404) | HIGH | Phase 1 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | nginx 404 for probes + SeoProvider noindex on unknown paths. [Better than before; full fix not possible without SSR.]
MAF-TECH-006 | No HTTP→HTTPS, non-www→www redirects | HIGH | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Deploy nginx redirect rules. [All traffic goes to https://www.mafateehgroup.com.]
MAF-TECH-013 | No code splitting | HIGH | Phase 2 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | vite.config.js manualChunks + lazy routes in App.jsx. [Each page downloads only what it needs.]
MAF-TECH-017 | No OG/Twitter Card tags | HIGH | Phase 2 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Static OG in index.html + dynamic SeoProvider tags. [Social sharing previews are configured.]
MAF-TECH-018 | JS bundle too large (~2.5MB) | HIGH | Phase 3 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Splitting applied; full sub-500KB target unrealistic for current feature set. [Improved speed without removing features.]
MAF-TECH-019 | No browser/CDN caching | HIGH | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | nginx Cache-Control + CDN-Cache-Control headers. [Files are stored locally on repeat visits.]
MAF-TECH-022 | Estimated poor LCP (>2.5s) | HIGH | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Performance optimizations applied Aug 2026 incl. ParticleField and WebP. [Page load speed improved through multiple fixes.]
MAF-TECH-023 | Estimated poor TBT (>200ms) | HIGH | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Code splitting + animation performance fixes. [Smoother interaction during page load.]
MAF-TECH-038 | html lang="en" hardcoded | HIGH | Phase 2 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | index.html inline script + SeoProvider locale sync. [Language direction set correctly for each version.]
MAF-TECH-049 | Missing critical security headers | HIGH | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | nginx add_header directives on website container. [Security headers active on all responses.]
MAF-TECH-008 | Potential crawl trap | MEDIUM | Phase 1 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Combined with soft-404 mitigation. [Reduces risk of Google wasting crawl budget.]
MAF-TECH-009 | /blog returns 404 | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | nginx location = /blog return 301. [Legacy URL redirected correctly.]
MAF-TECH-011 | Blog post routes unverified | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | BlogPost.jsx + locale routes + redirect on 404. [Blog URLs work and handle missing posts gracefully.]
MAF-TECH-020 | Cloudflare edge cache unused | MEDIUM | Phase 1 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Origin headers done; Cloudflare UI rules pending (~5 min). [Half done in code; final step is a Cloudflare login task.]
MAF-TECH-021 | Assets lack long-cache URLs | MEDIUM | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Vite hashing + nginx /assets/ cache policy. [Long-term caching without stale updates.]
MAF-TECH-024 | Font loading not optimized | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | index.html preconnect, preload, display=swap. [Fonts load without blocking page text.]
MAF-TECH-025 | Same large bundle on mobile | MEDIUM | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Lazy-loaded routes reduce mobile payload on navigation. [Mobile performance improved within React limits.]
MAF-TECH-026 | Mobile-first indexing readiness (CSR) | MEDIUM | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Mobile-first indexing supported via Google JS rendering + responsive design. [Mobile search compatibility acceptable for React SPA.]
MAF-TECH-028 | Missing sameAs/social URLs | MEDIUM | — | PENDING | Marketing | 2026-08-18 | 2026-08-11 |  | Code supports sameAs; data entry pending. [Dev done — marketing adds the social links.]
MAF-TECH-030 | No cookie consent | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | CookieConsent.jsx + /cookie-policy pages + gated gtag. [Privacy-compliant analytics loading.]
MAF-TECH-032 | No accessibility statement [T051 merged] | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | AccessibilityStatement.jsx + localized content. [Accessibility information page is live.]
MAF-TECH-040 | Conversion events unverifiable | MEDIUM | — | PARTIALLY RESOLVED | Marketing | 2026-08-18 | 2026-08-11 | 2026-08-18 | Events in ContactForm.jsx and SiteShell.jsx; GA4 verification pending. [Dev installed tracking; marketing checks the dashboard.]
MAF-TECH-042 | Logo too large (~307KB) | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | website/public/logo-mafateeh.png. Evidence: closure-evidence/logo-size.txt
MAF-TECH-043 | Portfolio images unverified | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | backend imageOptimize.ts + optimizedImageUrl.js on frontend. [Automatic image optimization pipeline.]
MAF-TECH-044 | No responsive images/WebP | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | optimizedImageUrl.js on BlogCard, PortfolioCard, BlogPostArticle. [Right-size images on every device.]
MAF-TECH-046 | Google Fonts render-blocking | MEDIUM | Phase 3 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Font preload strategy in index.html. [Fonts no longer block first text display.]
MAF-TECH-050 | A11y baseline unverifiable (CSR) | MEDIUM | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Statement page live; raw-HTML a11y audit limitation accepted with React. [Compliance page done; deep audit is a separate test.]
MAF-TECH-052 | Technical debt accumulating | MEDIUM | Phase 2 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Major SEO/perf debt addressed Aug 2026. SSR debt consciously deferred. [Project is healthier; full rewrite not needed.]
MAF-TECH-010 | No dedicated contact page | LOW | — | ALREADY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Contact page predates audit. [No work needed — page already live.]
MAF-TECH-031 | No Terms & Conditions | LOW | — | PARTIALLY RESOLVED | IT Dev + Marketing | 2026-08-18 | 2026-08-11 | 2026-08-18 | TermsAndConditions model + admin UI.
MAF-TECH-033 | No .ico favicon | LOW | — | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | public/favicon.ico + favicon.svg. [Browser tab icon fixed.]
MAF-TECH-034 | No web app manifest | LOW | — | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | public/site.webmanifest + nginx location. [Mobile install metadata available.]
MAF-TECH-035 | System paths return SPA shell | LOW | Phase 1 | PARTIALLY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | nginx probe 404 blocks implemented. [Security scans get proper errors.]
MAF-TECH-039 | No analytics in raw HTML | LOW | — | NOT APPLICABLE | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Consent-gated analytics by design. [This “issue” is actually correct behavior.]
MAF-TECH-041 | No lead capture forms | LOW | — | ALREADY RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | ContactForm.jsx + booking link on contact page. [Forms already live.]
MAF-TECH-045 | Favicon MIME type mismatch | LOW | — | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Proper favicon.ico + favicon.svg files. [Icon format mismatch fixed.]
MAF-TECH-047 | Google Fonts not self-hosted | LOW | — | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | main.jsx @fontsource imports; removed Google Fonts from index.html. Evidence: fonts-self-hosted.txt
MAF-TECH-048 | HSTS header not set ⚠️ SUB-ITEM of T049 | SUB-ITEM | Phase 1 | RESOLVED | IT Dev | 2026-08-18 | 2026-08-11 | 2026-08-18 | Included in security headers deployment. [Secure connection enforced.]

## 5. Verify Tracker
Issue ID | Title | Severity | Verify Status | Before Evidence | After Evidence | Verified By | Verify Date | Result | Notes
MAF-TECH-001 | robots.txt returns HTML SPA shell | CRITICAL | VERIFIED (CODE) | See audit files | public/robots.txt + nginx.default.conf location = /robots.txt | IT Dev Team | 2026-08-18 | PASS | File exists in repo; nginx serves text/plain. Post-deploy live check recommended. [Confirmed in code; quick live test after release.]
MAF-TECH-003 | No canonical link tag | CRITICAL | VERIFIED (CODE) | See audit files | SeoProvider.jsx + index.html canonical | IT Dev Team | 2026-08-18 | PASS | Canonical logic confirmed in SeoProvider. [Built into the site; verify on live URLs after deploy.]
MAF-TECH-012 | Full CSR — content invisible without JS | CRITICAL | PARTIALLY VERIFIED | See audit files | Static meta/JSON-LD + bilingual routes | IT Dev Team | 2026-08-18 | PARTIAL | Mitigations in code; full CSR limitation accepted. [Not a full fix, but acceptable given we stay on React.]
MAF-TECH-027 | No structured data (JSON-LD) | CRITICAL | VERIFIED (CODE) | See audit files | index.html + SeoProvider JSON-LD blocks | IT Dev Team | 2026-08-18 | PASS | JSON-LD present in HTML and SeoProvider. [Ready for Google’s structured-data checker after go-live.]
MAF-TECH-036 | Arabic content not discoverable (state i18n) | CRITICAL | VERIFIED (CODE) | See audit files | /en/* /ar/* routes + sitemap hreflang | IT Dev Team | 2026-08-18 | PASS | Routes, sitemap, and hreflang confirmed in repo. [Both languages have their own URLs in the sitemap.]
MAF-TECH-002 | No XML sitemap | HIGH | VERIFIED (CODE) | See audit files | public/sitemap.xml | IT Dev Team | 2026-08-18 | PASS | sitemap.xml in repo with bilingual entries. [File ready; Marketing to submit in GSC.]
MAF-TECH-004 | Index status unverifiable | HIGH | PENDING EXTERNAL | See audit files | Awaiting GSC access | IT Dev Team |  | PENDING | Requires Google Search Console — no IT Ops team; Marketing to action. [Someone with Google account access must complete this step.]
MAF-TECH-005 | All paths HTTP 200 (soft-404) | HIGH | PARTIALLY VERIFIED | See audit files | nginx probe blocks + SeoProvider noindex | IT Dev Team | 2026-08-18 | PARTIAL | Probe 404s and noindex logic in code. [Security probe paths fixed; some invalid URLs still return 200 by design.]
MAF-TECH-006 | No HTTP→HTTPS, non-www→www redirects | HIGH | VERIFIED (CODE) | See audit files | deploy nginx HTTPS/www redirects | IT Dev Team | 2026-08-18 | PASS | Redirect config in deploy nginx. [Standard security redirect — confirm with browser after deploy.]
MAF-TECH-013 | No code splitting | HIGH | VERIFIED (CODE) | See audit files | Vite chunks + React.lazy routes | IT Dev Team | 2026-08-18 | PASS | Build produces separate chunks. [Confirmed in build output.]
MAF-TECH-017 | No OG/Twitter Card tags | HIGH | VERIFIED (CODE) | See audit files | index.html + SeoProvider OG/Twitter | IT Dev Team | 2026-08-18 | PASS | OG/Twitter tags in HTML and SeoProvider. [Use Facebook/LinkedIn debug tools after deploy.]
MAF-TECH-018 | JS bundle too large (~2.5MB) | HIGH | PARTIALLY VERIFIED | See audit files | Vite build chunk sizes | IT Dev Team | 2026-08-18 | PARTIAL | Chunks reduced vs monolith; measure post-deploy. [Better, not perfect — normal for React sites.]
MAF-TECH-019 | No browser/CDN caching | HIGH | VERIFIED (CODE) | See audit files | nginx caching headers | IT Dev Team | 2026-08-18 | PASS | Caching rules in nginx.default.conf. [Check response headers after deploy.]
MAF-TECH-022 | Estimated poor LCP (>2.5s) | HIGH | NOT VERIFIED | See audit files | Splitting, WebP, font preload, animation tuning | IT Dev Team |  | PENDING MEASUREMENT | Lab estimate only — needs Lighthouse/PageSpeed on production. [Dev improvements done; marketing can run speed test after launch.]
MAF-TECH-023 | Estimated poor TBT (>200ms) | HIGH | NOT VERIFIED | See audit files | Code splitting + reduced GPU load | IT Dev Team |  | PENDING MEASUREMENT | Lab estimate — verify with Lighthouse post-deploy. [Needs a speed test on the live website.]
MAF-TECH-038 | html lang="en" hardcoded | HIGH | VERIFIED (CODE) | See audit files | index.html + locale routing | IT Dev Team | 2026-08-18 | PASS | lang/dir logic in index.html and LanguageProvider. [Arabic pages show dir=rtl.]
MAF-TECH-049 | Missing critical security headers | HIGH | VERIFIED (CODE) | See audit files | nginx security headers incl. HSTS | IT Dev Team | 2026-08-18 | PASS | Headers defined in nginx.default.conf. [Can be checked with free online header tools.]
MAF-TECH-008 | Potential crawl trap | MEDIUM | PARTIALLY VERIFIED | See audit files | Same as MAF-TECH-005 | IT Dev Team | 2026-08-18 | PARTIAL | Probe blocks + noindex in place. [Partial protection in place.]
MAF-TECH-009 | /blog returns 404 | MEDIUM | VERIFIED (CODE) | See audit files | nginx /blog → /en/blogs | IT Dev Team | 2026-08-18 | PASS | Redirect in nginx.default.conf. [Old /blog address forwards to blogs page.]
MAF-TECH-011 | Blog post routes unverified | MEDIUM | VERIFIED (CODE) | See audit files | App.jsx blog routes + BlogPost redirect | IT Dev Team | 2026-08-18 | PASS | Routes and error handling confirmed. [Blog links work; test with a real post after deploy.]
MAF-TECH-020 | Cloudflare edge cache unused | MEDIUM | PENDING EXTERNAL | See audit files | nginx CDN-Cache-Control + CACHE_RULES.md guide | IT Dev Team |  | PENDING | Origin ready; Cloudflare dashboard config outstanding. [Dev team finished their part; Cloudflare account holder must finish.]
MAF-TECH-021 | Assets lack long-cache URLs | MEDIUM | VERIFIED (CODE) | See audit files | /assets/* immutable cache | IT Dev Team | 2026-08-18 | PASS | Hashed filenames in build output. [Standard modern web practice — confirmed.]
MAF-TECH-024 | Font loading not optimized | MEDIUM | VERIFIED (CODE) | See audit files | index.html font preload + swap | IT Dev Team | 2026-08-18 | PASS | Font loading strategy in index.html. [Visitors see text right away.]
MAF-TECH-025 | Same large bundle on mobile | MEDIUM | PARTIALLY VERIFIED | See audit files | React.lazy per route | IT Dev Team | 2026-08-18 | PARTIAL | Lazy routes confirmed; shared React core remains. [Better mobile loading, not identical to a lightweight static site.]
MAF-TECH-026 | Mobile-first indexing readiness (CSR) | MEDIUM | PARTIALLY VERIFIED | See audit files | Responsive site + SEO mitigations | IT Dev Team | 2026-08-18 | PARTIAL | Google renders JS; no SSR planned. [Works with Google’s mobile indexing; not ideal but accepted.]
MAF-TECH-028 | Missing sameAs/social URLs | MEDIUM | PENDING EXTERNAL | See audit files | SeoProvider sameAs from Static Info API | IT Dev Team |  | PENDING | Awaiting social URLs from business. [Google can show social icons once links are entered.]
MAF-TECH-030 | No cookie consent | MEDIUM | VERIFIED (CODE) | See audit files | CookieConsent + conditional gtag load | IT Dev Team | 2026-08-18 | PASS | Banner and gating confirmed in SeoProvider. [Analytics only runs after user clicks Accept.]
MAF-TECH-032 | No accessibility statement [T051 merged] | MEDIUM | VERIFIED (CODE) | See audit files | /en/accessibility /ar/accessibility | IT Dev Team | 2026-08-18 | PASS | Pages and footer links confirmed. [Page exists; content review optional.]
MAF-TECH-040 | Conversion events unverifiable | MEDIUM | PENDING EXTERNAL | See audit files | gtag generate_lead + contact events | IT Dev Team |  | PENDING | Code complete; needs GA4 login to confirm. [Someone with Analytics access must test form submission.]
MAF-TECH-042 | Logo too large (~307KB) | MEDIUM | VERIFIED (CODE) | See audit files | Compressed logo-mafateeh.png | IT Dev Team | 2026-08-18 | PASS | File size 40020 bytes < 50 KB.
MAF-TECH-043 | Portfolio images unverified | MEDIUM | VERIFIED (CODE) | See audit files | sharp upload + Cloudinary srcset | IT Dev Team | 2026-08-18 | PASS | Upload pipeline and srcset confirmed. [New uploads optimized; legacy images served responsively.]
MAF-TECH-044 | No responsive images/WebP | MEDIUM | VERIFIED (CODE) | See audit files | Cloudinary f_auto/srcset on image components | IT Dev Team | 2026-08-18 | PASS | srcset and lazy loading in components. [Mobile gets smaller images; desktop gets full quality.]
MAF-TECH-046 | Google Fonts render-blocking | MEDIUM | VERIFIED (CODE) | See audit files | index.html font strategy | IT Dev Team | 2026-08-18 | PASS | Preload + swap confirmed. [Same as font optimization fix.]
MAF-TECH-050 | A11y baseline unverifiable (CSR) | MEDIUM | PARTIALLY VERIFIED | See audit files | Accessibility statement + semantic components | IT Dev Team | 2026-08-18 | PARTIAL | Statement exists; full baseline needs live Lighthouse run. [Page added; formal score test can be run later.]
MAF-TECH-052 | Technical debt accumulating | MEDIUM | PARTIALLY VERIFIED | See audit files | Phase 1–3 SEO implementation complete | IT Dev Team | 2026-08-18 | PARTIAL | Multiple fixes shipped; CSR trade-off documented. [Debt reduced significantly within chosen architecture.]
MAF-TECH-010 | No dedicated contact page | LOW | VERIFIED (CODE) | See audit files | /en/contact /ar/contact live | IT Dev Team | 2026-08-18 | N/A — FALSE POSITIVE | Contact.jsx route confirmed. [Audit was wrong on this point.]
MAF-TECH-031 | No Terms & Conditions | LOW | VERIFIED (CODE) | See audit files | TermsAndConditions page + admin | IT Dev Team | 2026-08-18 | PASS — CONTENT PENDING | Page and editor in repo.
MAF-TECH-033 | No .ico favicon | LOW | VERIFIED (CODE) | See audit files | favicon.ico + favicon.svg | IT Dev Team | 2026-08-18 | PASS | Favicon files in public/. [Standard browser icon present.]
MAF-TECH-034 | No web app manifest | LOW | VERIFIED (CODE) | See audit files | site.webmanifest | IT Dev Team | 2026-08-18 | PASS | Manifest file confirmed. [Mobile browsers can recognize the site.]
MAF-TECH-035 | System paths return SPA shell | LOW | PARTIALLY VERIFIED | See audit files | nginx probe location blocks | IT Dev Team | 2026-08-18 | PARTIAL | Probe paths return 404. [Main security concern addressed.]
MAF-TECH-039 | No analytics in raw HTML | LOW | N/A | See audit files | SeoProvider conditional gtag | IT Dev Team |  | N/A — BY DESIGN | gtag loads post-consent only. [Analytics after Accept is intentional.]
MAF-TECH-041 | No lead capture forms | LOW | VERIFIED (CODE) | See audit files | ContactForm + calendar booking | IT Dev Team | 2026-08-18 | N/A — FALSE POSITIVE | Contact form confirmed in codebase. [Audit was wrong.]
MAF-TECH-045 | Favicon MIME type mismatch | LOW | VERIFIED (CODE) | See audit files | favicon.ico + favicon.svg correct types | IT Dev Team | 2026-08-18 | PASS | Correct file types in public/. [Technical favicon issue resolved.]
MAF-TECH-047 | Google Fonts not self-hosted | LOW | VERIFIED (CODE) | See audit files | website/src/main.jsx @fontsource imports | IT Dev Team | 2026-08-18 | PASS | grep confirms zero fonts.googleapis.com in public website.
MAF-TECH-048 | HSTS header not set ⚠️ SUB-ITEM of T049 | SUB-ITEM | VERIFIED (CODE) | See audit files | HSTS header in nginx | IT Dev Team | 2026-08-18 | PASS | HSTS in deploy nginx. [Covered by MAF-TECH-049 fix.]

## 6. Gap Analysis
Issue ID | Title | Severity | Gap Type | What's Missing | Required Access/Action | Verification Requirement
MAF-TECH-004 | Index unverifiable | HIGH | ⚠️ NEEDS GSC | Google Search Console | Developer: add property + verify DNS | GSC Index Coverage report
MAF-TECH-022 | Poor LCP | HIGH | 📋 LAB ESTIMATE | CrUX field data | GSC Core Web Vitals OR RUM | LCP < 2.5s
MAF-TECH-023 | Poor TBT | HIGH | 📋 LAB ESTIMATE | CrUX field data | GSC Core Web Vitals OR RUM | TBT < 200ms
MAF-TECH-027 | No structured data | CRITICAL | ✅ CODE DONE — RICH RESULTS PENDING | Production Rich Results Test validation | Developer: run Google Rich Results Test after deploy | Rich Results Test PASS on production URL
MAF-TECH-011 | Blog routes unverified | MEDIUM | ✅ CODE DONE | — | Routes verified in App.jsx / BlogPost.jsx | Blog slug routes + redirect on missing post
MAF-TECH-026 | Mobile-first indexing | MEDIUM | ⚠️ ANALYSIS GAP | GSC mobile vs desktop index | GSC access | Mobile/desktop index parity
MAF-TECH-028 | Missing sameAs | MEDIUM | 🏢 NEEDS BUSINESS | Official social URLs | Business: confirm all URLs | All social profiles in JSON-LD
MAF-TECH-031 | No T&C | LOW | 🏢 NEEDS BUSINESS | Legal requirement (Jordan) | Business/Legal: jurisdiction check | T&C page present if required
MAF-TECH-040 | Conversion unverifiable | MEDIUM | ⚠️ NEEDS GA4 | GA4/GTM access | Developer: add GA4 snippet | Conversion events firing
MAF-TECH-043 | Portfolio images | MEDIUM | ✅ CODE DONE — legacy audit optional | Optional re-upload of very large legacy images | Marketing: optional legacy image review | Upload pipeline + Cloudinary srcset in code
MAF-TECH-050 | A11y baseline | MEDIUM | ⚠️ PARTIAL | Production axe/Lighthouse a11y score | Run Lighthouse accessibility after deploy | Accessibility statement live + optional audit
MAF-TECH-039 | No analytics | LOW | N/A — BY DESIGN | Analytics must load after cookie consent | No change — proof under MAF-TECH-040 | gtag loads only after Accept (SeoProvider)

## 7. Repair Manifest
Repair ID | Repair Name | Issues Solved | Type | Phase | Effort | Status | Notes | Alternative Artifacts
AR-001 | robots.txt | 001 | Static file | 1 | 15 min | COMPLETED | robots.txt deployed as static file. [Crawl rules file is live.]
AR-002 | sitemap.xml | 002 | Static file | 1 | 1h | COMPLETED | sitemap.xml with bilingual URLs deployed. [Site map for Google is live.]
AR-003 | Nginx — static files | 001,002 | Nginx | 1 | 15 min | COMPLETED | Nginx serves robots.txt and sitemap as real files, not SPA. [Server correctly delivers SEO files.]
AR-004 | Nginx — redirects | 006 | Nginx | 1 | 15 min | COMPLETED | HTTP→HTTPS and apex→www redirects in deploy nginx. [Traffic goes to correct secure URL.]
AR-005 | Nginx — route whitelist | 005,008,035 | Nginx | 1 | 30 min | PARTIALLY COMPLETED | Probe paths 404 + noindex on unknown SPA routes. Full whitelist needs SSR. [Partial soft-404 fix applied.]
AR-006 | Nginx — caching | 019,021 (020 pending Cloudflare) | Nginx | 1 | 15 min | PARTIALLY COMPLETED | Origin cache headers COMPLETED for 019/021. MAF-TECH-020 Cloudflare dashboard rules + cache HIT proof remain PENDING EXTERNAL. [Server ready; Cloudflare login task ~5 min.] | —
AR-007 | Nginx — security headers | 048,049 | Nginx | 1 | 15 min | COMPLETED | Security headers including HSTS deployed. [Security headers active.]
AR-008 | Canonical tags | 003 | React | 1 | 1h | COMPLETED | Canonical tags via SeoProvider + index.html. [Official URLs set per page.]
AR-009 | Organization JSON-LD | 027 (028 pending business URLs) | HTML | 2 | 2h | PARTIALLY COMPLETED | Organization JSON-LD wired in HTML + SeoProvider for 027. MAF-TECH-028 sameAs awaits Marketing social URLs in Static Info. [Code ready; marketing adds links.] | —
AR-010 | WebSite JSON-LD | 027 | HTML | 2 | 30 min | COMPLETED | WebSite JSON-LD on homepage via SeoProvider. [Homepage schema added.]
AR-011 | Breadcrumb JSON-LD | 027 | HTML | 2 | 30 min | COMPLETED | BreadcrumbList JSON-LD per route. [Navigation breadcrumbs for search.]
AR-012 | OG/Twitter tags | 017 | React | 2 | 1h | COMPLETED | OG/Twitter tags static + dynamic. [Social sharing previews configured.]
AR-013 | i18n URL routing | 036 | Architecture | 2 | 2-3d | COMPLETED | /en and /ar URL routing with legacy redirects. [Bilingual URLs implemented without SSR.]
AR-014 | hreflang + lang sync | 036,038 | React | 2 | 1h | COMPLETED | hreflang + lang/dir sync for EN/AR. [Language signals for Google.]
AR-015 | Code splitting | 013,023,025 | Vite/React | 2 | 4-8h | COMPLETED | Vite manualChunks + React.lazy code splitting. [Faster page loads via split bundles.]
AR-016 | Next.js SSR | — (cancelled) | Architecture | 2 | 2-4w | CANCELLED | Next.js SSR rejected — business decision to keep React SPA. NOT used as closure evidence. | 012→meta/JSON-LD/sitemap ¦ 022→splitting/WebP/fonts ¦ 026→responsive+JS indexing ¦ 027→SeoProvider JSON-LD ¦ 036→/en /ar routes ¦ 038→lang/dir ¦ 050→a11y statement ¦ 052→debt reduction plan
AR-017 | Font optimization | 024,046 (047 self-hosted separately) | Build | 3 | 1h | COMPLETED | Font preload + display=swap for 024/046. MAF-TECH-047 resolved separately via @fontsource self-hosting (no Google Fonts requests). [Fonts now served from site bundle.] | 047→website/src/main.jsx @fontsource imports
AR-018 | Image optimization | 042,043,044 | Build | 3 | 4h | COMPLETED | Logo compression, upload pipeline sharp/WebP, Cloudinary srcset. [Image optimization complete.]

## 8. Summary
MAFATEEH GROUP — FINAL RECONCILED MASTER REGISTER
Metric | Value
T12 Raw Rows | 46
Unique Issues | 44
Sub-items | 1 (MAF-TECH-048 → T049)
True Duplicates | 1 (MAF-TECH-051 → T032)
Final Register Entries | 45 (44 unique + 1 sub-item)
CRITICAL | 5
HIGH | 12
MEDIUM | 18
LOW | 9
Gap/Unverified | 12
Root Causes | 5
Repair Artifacts | 18
Implementation Status | RESOLVED: 26 ¦ PARTIALLY RESOLVED: 13 ¦ PENDING: 2 ¦ ALREADY RESOLVED: 2 ¦ NOT APPLICABLE: 2
Verification Status | VERIFIED (CODE): 28 ¦ PARTIALLY VERIFIED: 9 ¦ PENDING EXTERNAL: 4 ¦ NOT VERIFIED: 2 ¦ N/A: 2
Production / Deployment Status | Implementation deployed; code-level verification completed where recorded. Post-deployment, production, and external verification remain pending. Final acceptance is not yet complete.
Developer Decisions | APPROVE: 26 ¦ MODIFY: 11 ¦ REJECT: 4 ¦ FURTHER INVESTIGATION: 4
Team Structure Note | No dedicated IT Ops — IT Dev owns code/nginx; Marketing owns GSC, GA4, Cloudflare UI, social URLs, and legal content. [Dev builds; marketing verifies and fills business data.]
Last Updated | 2026-08-17
Developer Decisions | APPROVE: 26 ¦ MODIFY: 11 ¦ REJECT: 4 ¦ FURTHER INVESTIGATION: 4
Team Structure Note | No dedicated IT Ops — IT Dev owns code/nginx; Marketing owns GSC, GA4, Cloudflare UI, social URLs, and legal content. [Dev builds; marketing verifies and fills business data.]
Last Updated | 2026-08-17

## 9. Change Log
Sheet | Issue / Artifact | Field | Old Value | New Value | Reason | Evidence Reference
2. HML Matrix | MAF-TECH-012 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL — CSR mitigated | Conflict fix per closure report §3 | SeoProvider + index.html
2. HML Matrix | MAF-TECH-005 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL — probe 404 + noindex | Conflict fix | http-route-tests.txt
2. HML Matrix | MAF-TECH-018 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL — bundle reduced | Conflict fix | build-output.txt
2. HML Matrix | MAF-TECH-008 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL | Conflict fix | http-route-tests.txt
2. HML Matrix | MAF-TECH-025 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL | Conflict fix | build-output.txt
2. HML Matrix | MAF-TECH-052 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL | Conflict fix | Closure report §3
2. HML Matrix | MAF-TECH-035 | Gap Type | ✅ VERIFIED | ⚠️ PARTIAL | Conflict fix | http-route-tests.txt
2. HML Matrix | MAF-TECH-020 | Gap Type | ✅ VERIFIED | ⚠️ PENDING EXTERNAL | Conflict fix | CACHE_RULES.md
2. HML Matrix | MAF-TECH-027 | Gap Type | 🔧 NEEDS DEV | ✅ CODE DONE — Rich Results pending | Conflict fix | index.html JSON-LD
2. HML Matrix | MAF-TECH-039 | Gap Type | 🔧 NEEDS DEV | N/A — BY DESIGN | Conflict fix | SeoProvider gtag gate
2. HML Matrix | MAF-TECH-047 | Gap Type | ✅ VERIFIED | ✅ CODE DONE — self-hosted | Self-host fonts implemented | fonts-self-hosted.txt
6. Gap Analysis | MAF-TECH-027 | Gap Type | 🔧 NEEDS DEV | ✅ CODE DONE — RICH RESULTS PENDING | Conflict fix | SeoProvider
6. Gap Analysis | MAF-TECH-039 | Gap Type | 🔧 NEEDS DEV | N/A — BY DESIGN | Conflict fix | CookieConsent
7. Repair Manifest | AR-006 | Status/Issues | COMPLETED / 019,020,021 | PARTIALLY COMPLETED / 019,021 | 020 split pending Cloudflare | CACHE_RULES.md
7. Repair Manifest | AR-009 | Status/Issues | COMPLETED / 027,028 | PARTIALLY COMPLETED / 027 | 028 pending business URLs | SeoProvider sameAs
7. Repair Manifest | AR-016 | Issues Solved | 012,022,026,027,036,038,050,052 | — (cancelled) | Remove as closure proof | Alternative artifacts column
7. Repair Manifest | AR-017 | Issues Solved | 024,046,047 | 024,046 (047 separate) | 047 not direct AR-017 repair | main.jsx @fontsource
8. Summary | Implementation Status | aggregated | RESOLVED 26 ¦ PARTIAL 13 ¦ ... | RESOLVED 27 ¦ PARTIAL 12 ¦ PENDING 2 ¦ ALREADY RESOLVED 2 ¦ N/A 2 | Reconciled counts | Issue-level export
8. Summary | Verification Status | aggregated | CODE VERIFIED 28 ¦ ... | VERIFIED (CODE) 28 ¦ PARTIAL 9 ¦ PENDING 4 ¦ NOT VERIFIED 2 ¦ N/A 2 | Reconciled counts | Issue-level export
8. Summary | Production Changes | DEPLOYED/READY | Implementation deployed; code-level verification completed where recorded. Post-deployment, production, and external verification remain pending. Final acceptance is not yet complete. | Closure report §2.B wording | Summary
Code | MAF-TECH-047 | Implementation | REJECT / Google Fonts | Self-host @fontsource | Option 1 implemented | main.jsx + index.html
Code | MAF-TECH-042 | Logo size | 82 KB | 40 KB PNG / 24 KB WebP | Under 50 KB target | logo-size.txt